Design & Innovation Project (DIP)

Project Charter

Large Language Model Assisted Control Design and Auto Tuning for Underactuated Robotic Systems

Project Group: E026

School of Electrical and Electronic Engineering

Academic Year 2026/27

Semester 1/2

Revision dated 4 September 2026. Yellow highlighting identifies revised or added text. Word comments explain the changes. A revision map is included at the end.

| Date Prepared: | 2026.9.3 |
| --- | --- |

| Project Name: | Large Language Model Assisted Control Design and Auto Tuning for Underactuated Robotic Systems |
| --- | --- |
| Project Supervisor: | Professor Xie Lihua |
| Project Manager: | He Song Rui |
| Treasurer: | Zheng Yuxin |

Project Purpose or Justification:

This project investigates large language models (LLMs) as assistants for control design and auto-tuning of an underactuated two-wheel self-balancing robot. Two teams develop complete, independent approaches: Pipeline A combines a harnessed LLM workflow with PID/LQR tuning; Pipeline B combines researcher-mediated, non-harness LLM interaction with reinforcement learning (RL) reward design.

The teams first establish a reproducible simulation environment, a verified common PID baseline, and fixed platform interfaces. Each team then owns its controller development, simulation validation, hardware deployment, and experiments. Deliverables include the shared benchmark, an automated PID/LQR tuning framework, a reproducible PPO reward-design and training workflow, validated controllers, safety mechanisms, and comparative results. The project evaluates the contribution of LLM assistance within each approach and the practical suitability of the two complete engineering solutions.

Project Description:

1. Overview

The project uses a Yahboom STM32 robot and a reproducible MuJoCo/Gymnasium simulation suite. Team A develops Harness + LLM-assisted PID/LQR tuning. Team B develops Non-harness + LLM-assisted RL reward design. Each team owns simulation, validation, and hardware deployment. Harness means programmatic LLM integration through structured interfaces, automated experiment execution, deterministic validation, and acceptance or rollback rules. Non-harness means researcher-mediated LLM interaction: members review and implement suggestions before launching experiments. The distinction concerns LLM integration, not online versus offline operation or the presence of safety mechanisms.

2. Non Harness Workflow for Pipeline B

Researchers provide selected PPO training logs and evaluation metrics to the LLM through dialogue, review its reward-design suggestions, and manually update versioned experiment configurations. Training, logging, and evaluation may be automated, but the LLM does not directly invoke the experiment execution system. The resulting compact PPO policy is validated and deployed as a bounded residual around the frozen common PID baseline. The LLM remains outside hardware operation.

3. Harness Workflow for Pipeline A

A programmatic harness summarises telemetry, calls the LLM through a structured API, validates proposed PID gains or LQR weights, runs simulation evaluations, and accepts or rolls back changes under predefined rules. Hardware deployment follows deterministic checks and supervised test approval. The STM32 retains the continuous real-time control loop; LLM calls run asynchronously off-board and never issue high-frequency motor commands.

The core deliverable is a reproducible episode-based automatic tuning loop. Short-window adaptation is an optional extension after this loop is validated. Both deployed approaches shall meet a 200 Hz control rate and a full sensor-to-output execution time below 5 ms; Pipeline B targets an MLP forward pass within 1.5 ms.

4. Comparison of the Two Approaches

Within Pipeline A, compare manual and LLM-assisted tuning using the same controller structure. Within Pipeline B, compare human-designed and LLM-assisted rewards using the same PPO architecture, frozen PID baseline, training budget, and seed set. Then compare the final approaches under common test conditions for control performance, compute requirements, development effort, and automation. The cross-pipeline comparison evaluates complete engineering approaches; it does not isolate the causal effect of harness versus non-harness interaction because the control methods also differ.

5. Methodology

First verify and version the common robot model, PID baseline, observation/action definitions, control timing, safety limits, telemetry schema, and evaluation scripts. Freeze these interfaces before independent development. Each team develops and validates its approach in simulation, passes safety and quantitative transferability gates, and performs supervised hardware trials. Shared-interface changes require versioning and agreement on whether comparative tests must be repeated. Neither team depends on the other team's evolving controller results.

6. Deliverables and Expected Outcome

Common deliverables are a reproducible simulation benchmark, instrumented robot, frozen baseline, safety interfaces, and evaluation protocol. Team A delivers its harness, tuned classical controller, deployment package, and manual-versus-LLM tuning experiments. Team B delivers reward-design interaction records, training configurations, compact PPO residual policies, deployment package, and human-versus-LLM reward experiments. Both contribute datasets, robustness tests, and a comparison of the complete approaches.

High-level Project and Product Requirements:

1. Hardware & Platform Specifications

- Target Platform: The system shall be implemented on a Yahboom STM32 two-wheel self-balancing robot.

- Operating Objective (0-degree regulation): The robot shall operate as an inverted pendulum, regulating its pitch angle to maintain a target 0-degree upright position.

- Resource Constraints: All deployed control policies and algorithms shall satisfy the computational, memory, motor-output, and control-loop limits of the STM32 microcontroller.

2. Dynamic Performance & Convergence Limits

- Convergence & Transient Response: Following a bounded initial disturbance (e.g. +/-10 degrees tilt), the control system shall return the pitch angle to the upright position with settling time < 1.5 s and maximum overshoot < 3 degrees.

- Steady-State Stability (Accounting for Hardware): Recognising motor backlash and IMU noise, the steady-state RMS tilt error shall be maintained within a realistic band of +/-1.0 to +/-1.5 degrees from the 0-degree setpoint.

- Control Loop Latency: Each deployed control cycle, including sensing, state estimation, and the applicable controller, shall execute in < 5 ms at a control frequency of at least 200 Hz. Pipeline B includes residual-policy inference within this budget and targets an MLP forward pass within 1.5 ms.

- Baseline-Relative Performance: Both approaches shall be evaluated against the frozen manually tuned PID baseline using common metrics, including steady-state error and motor PWM variance. Pipeline A shall also compare manual and LLM tuning of the same controller structure; Pipeline B shall compare human-designed and LLM-assisted rewards under matched PPO training conditions.

- RL Rapid Stabilisation (Pipeline B): The LLM-assisted PPO policy shall be evaluated from extreme initial pitch angles in [-40 degrees, +40 degrees] on flat ground and for recovery after manual disturbances. Final time-to-upright and recovery targets shall be benchmarked against baseline characterisation.

3. Control Architecture & Dual Pipelines

Pipeline A Harnessed LLM Assisted PID and LQR Tuning

Team A owns the programmatic tuning harness, classical controller, simulation validation, deployment, and evaluation. Fix the controller structure for each comparison and allow the LLM to propose only predefined PID gains or, where applicable, LQR weights within declared bounds.

- Core Tuning Loop: Summarise complete episodes using overshoot, settling time, steady-state error, and control effort. Automatically request structured LLM proposals, validate their schema and bounds, run simulation trials, and accept or roll back changes using predefined performance and safety criteria. Record every proposal and decision.

- Optional Short-Window Adaptation: After validating the core loop, summarise moving 0.5- to 1.0-second telemetry windows to support slower, bounded gain adjustments. This extension is not required for the core deliverable, and the LLM remains outside the high-frequency motor loop.

- Safety Gate: All metric-driven updates must pass parameter bounds, simulation validation, and hardware safety checks before deployment.

Pipeline B Non Harness LLM Assisted RL Reward Design

Team B owns researcher-mediated reward design, PPO training, simulation validation, compact-policy deployment, and evaluation. The core deliverable is one validated residual policy; a multi-skill library, policy selection, and interpolation are optional extensions.

- Non-Harness Training: Researchers select MuJoCo/Gymnasium PPO logs, discuss reward revisions with the LLM, review the suggestions, and manually update experiment configurations. The LLM does not invoke training tools. Candidate reward terms include angle, angular velocity, acceleration, control effort, position, survival, and disturbance resilience. Normalise component weights within [0, 1] with sum(w_i) = 1, and document term scaling and signs.

- Hardware Execution: Deploy the validated compact PPO policy as a bounded residual around the frozen common PID baseline. The LLM remains outside hardware operation and issues no real-time motor commands or reward updates. Apply deterministic output limits, timing checks, fallback, and emergency-stop protections.

- Baseline Independence: Version and freeze the common PID baseline during platform setup. Pipeline B shall not depend on later controller updates from Pipeline A. Use the same frozen baseline for both reward-design variants. Log every fallback event separately; baseline takeover shall not be counted as successful RL operation.

4. LLM Integration & Role

- Supervisory & Offline Constraint: The LLM shall function as an offline or asynchronous supervisory assistant. It shall not process the raw high-frequency sensor stream or generate high-frequency motor commands.

- Pipeline A Constraints: The harness shall use structured API inputs and outputs, bounded parameter proposals, deterministic validation, simulation evaluation, and explicit acceptance or rollback rules. Hardware changes require the applicable deployment safety checks.

- Pipeline B Constraints: Researchers shall review LLM suggestions before editing reward functions or agreed training settings. Archive prompts, responses, decisions, configuration versions, and seed sets. Match network architecture and training budget between reward variants; the deployed network must meet the 5 ms full-cycle budget.

- Architecture Selection: The two core architectures are a harnessed classical-control tuning loop and a researcher-mediated PPO reward-design workflow with bounded residual deployment. Safety checks apply to both. Online short-window adaptation and multi-skill control remain optional extensions and are reported separately from core comparisons.

5. Safety & Fallback Mechanisms

- Hardware Limits: Enforce maximum motor-output (PWM) saturation caps and maximum allowable-angle thresholds (e.g. +/-40 degrees before abort).

- Automated Fallback: A mathematically stable PID or LQR baseline shall remain available and automatically engage if unsafe behaviour, limit cycling, or constraint violations are detected.

- Emergency Protocols: Include a hard software kill-switch to immediately cut motor power if the tilt exceeds unrecoverable limits.

Project Management plan:

1. Executive Summary

The project develops two independent LLM-assisted control approaches for the Yahboom SBR-STM32 robot. Team A integrates the LLM into an automated, constrained PID/LQR tuning harness. Team B uses researcher-mediated LLM dialogue to refine PPO reward design and trains compact residual policies. Each team evaluates whether LLM assistance improves its own baseline workflow, then contributes to a common comparison of performance, development effort, automation, and deployment suitability.

2. Key Innovations and Sources of Opportunity

2.1 Key Innovations

2.1.1 LLM Assistance for Classical Control and Reward Design

Pipeline A tests whether structured LLM proposals reduce manual PID/LQR tuning effort while preserving or improving control performance. Pipeline B tests whether researcher-reviewed LLM reward suggestions improve PPO learning and final policy performance. Deterministic validation separates proposals from deployment in both approaches.

2.1.2 Independent Harness and Non Harness Approaches

Pipeline A embeds LLM calls within a programmatically orchestrated experimental loop. Pipeline B uses human-mediated LLM interaction, followed by researcher-approved experiment changes. Both teams use frozen platform interfaces and a common benchmark while developing independently. Non-harness training may automate PPO execution and evaluation without connecting the LLM to those tools.

2.1.3 Engineering Validator for Physical Underactuated Hardware

A shared validation foundation provides versioned robot interfaces, a frozen PID baseline, safety limits, logging, communication, and metric computation. Each team implements and validates its own controller and deployment package against these interfaces. Any common-interface change is reviewed and versioned before further comparative experiments.

2.1.4 RL Rapid Stabilisation Performance

The LLM-assisted PPO policy shall be evaluated on its ability to stabilise the robot from extreme initial pitch angles in [-40 degrees, +40 degrees] and to recover from disturbances during steady-state operation. Final performance targets will be benchmarked against baseline characterisation and refined before the final experiments.

2.2 Sources of Opportunity

Technological Maturity Inflection Point: The falling cost of LLM inference and improvements in code generation, data analysis, and reasoning make constrained control-engineering assistance increasingly practical.

Industrial Demand Gap: Conventional controller design relies heavily on expert knowledge and manual iterative tuning. AI-assisted design tools could reduce engineering effort, shorten tuning cycles, and improve adaptability.

Academic Research Gap: Existing work on LLM-assisted control is more mature for simulation and linear systems than for nonlinear, coupled, underactuated hardware. The project targets this underexplored deployment setting.

3. SMART Objectives

3.1 Objective 1: Baseline Controller Implementation

Specific: Implement, verify, and freeze a common PID controller on the STM32, together with platform interfaces, the simulation model, safety limits, and evaluation scripts. Pipeline A may additionally study LQR using a matched manually tuned LQR comparator; Pipeline B retains the frozen PID.

Measurable: balance success rate >= 95% over 60-second trials; maximum angular deviation <= 5 degrees.

Achievable: based on Yahboom official materials and established control theory. Relevant: provides the baseline for all LLM-enhanced comparisons.

Time-bound: complete by M2 (Sept. 16, 2026). Calendar dates in the Summary Milestones table govern the schedule; academic week labels are omitted until the team confirms the teaching calendar.

Test Conditions: random start-up conditions; 60-second trials; external disturbances permitted; provisional success definition based on return to equilibrium within 5 seconds following a disturbance.

3.2 Objective 2 Pipeline A Harness and Communication

Specific: Pipeline A shall receive structured performance metrics, call the LLM API, validate bounded PID/LQR proposals, run simulation evaluation, and accept or roll back updates. This objective concerns the automated harness, not Pipeline B's researcher-mediated reward discussions.

Measurable: end-to-end communication success rate >= 99%; proposal validation pass rate target >= 85%; average completed simulation tuning iteration <= 120 seconds. Record rejected proposals and timeouts. Do not weaken validation to achieve the pass-rate target.

Time-bound: harness prototype by M3 (Sept. 23, 2026); initial simulation validation by M5 (Oct. 7, 2026).

Test Conditions: 100 simulation iterations with randomised initial conditions.

3.3 Objective 3A: Auto-Tuning Demonstration

Simulation Fidelity & Sim-to-Real Transferability: The MuJoCo/Gymnasium environment shall replicate relevant robot dynamics, including mass distribution, wheel/motor torque limits, IMU noise characteristics, and control-loop timing. Domain randomisation (mass, friction, battery voltage, sensor noise) shall be applied to reduce the sim-to-real gap, and a quantitative transferability check shall be completed before hardware deployment.

Specific: Pipeline A shall compare harnessed LLM tuning against manual tuning of the same PID or LQR structure under matched test conditions. Record LLM calls, token cost, experiment count, and researcher time in addition to control performance.

Improvement targets: settling-time reduction >= 30%; maximum-overshoot reduction >= 40%; steady-state-error reduction >= 50%, relative to the matched manually tuned controller. These are research targets subject to baseline characterisation, distinct from common safety and performance requirements. Report absolute results and unmet targets. Initial validation by M5 (Oct. 7); final experiments by M7 (Oct. 23, 2026).

Test Scenarios: step response (velocity setpoint 0 -> 0.5 m/s); pulse-disturbance response (0.5 N s pulse torque).

Measurement Method: 10 repeated trials per configuration using a unified metric script and matched initial conditions. Report mean and variability, safety violations, fallback events, tuning cost, and researcher effort. Use frozen configurations for final comparisons.

3.4 Objective 3B Non Harness LLM Assisted RL Reward Design

Specific: Pipeline B shall compare PPO trained with a human-designed reward against PPO trained with a researcher-reviewed, LLM-assisted reward. Hold the network, frozen PID baseline, training budget, random seed set, and evaluation conditions fixed. Record any exploratory training-setting changes separately. Evaluate extreme-angle stabilisation and disturbance recovery after simulation and hardware safety gates.

Performance targets: time-to-upright from +/-40 degrees <= 2.5 s, with the original PID reference target <= 3 s to be measured; disturbance success rate >= 85%; steady-state RMS error <= 1.2 degrees; stable training within an initial 100K-step budget. These targets are subject to baseline and safety characterisation. Compare physical metrics across reward variants because different reward scales make raw returns non-comparable.

Time-bound: PPO baseline and human-designed reward by M4 (Sept. 23, 2026); initial LLM-assisted reward training and evaluation by M6 (Oct. 7); final experiments by M7 (Oct. 23).

Test Scenarios: (A) cold start at +40 degrees, zero angular velocity; (B) cold start at -40 degrees, zero angular velocity; (C) warm start at +/-40 degrees with +/-10 degrees/s angular velocity and manual disturbance at t = 0.5 s; (D) robustness under payload-induced centre-of-gravity shift.

Measurement Method: 10 independent evaluation trials per scenario. Log theta(t), omega(t), and u(t); compute time-to-upright, peak overshoot, settling time, IAE, and total variation of control. Record training seeds, steps, compute time, LLM interactions, human revisions, and fallback events. Report variability; do not count baseline takeover as RL success.

3.5 Objective 4: Robustness Validation

Specific: Each team shall validate its final controller under the same payload configurations and common safety protocol, using its own deployment package.

Measurable: success rate >= 80% under at least 3 distinct payload configurations.

Achievable: systematic tests with incremental mass additions.

Relevant: demonstrates performance beyond nominal conditions.

Time-bound: complete by M8 (Oct. 23, 2026). Payload configurations: 50 g, 100 g, and 150 g mass blocks fixed at different chassis positions to produce centre-of-gravity shifts.

3.6 Objective 5: Final Report Delivery

Specific: Complete a comprehensive final project report.

Measurable: minimum 40 pages covering literature review, methodology, experimental design, results, discussion, and conclusions.

Achievable: systematic documentation throughout the project.

Relevant: primary project deliverable and knowledge-transfer mechanism.

Time-bound: complete by M9 (Oct. 30, 2026). Include both within-pipeline LLM comparisons and the cross-pipeline comparison of complete approaches. Do not attribute cross-pipeline differences solely to harness versus non-harness interaction. If results warrant, the team may prepare an academic paper submission.

4. Meeting and Reporting Mechanisms

Weekly Team Meeting: Every Wednesday at 13:30. Team A (Sridhar, Tze Jun, Yuxin) reports the complete Harness + PID/LQR pipeline; Team B (Jiang Li, Jiayi, Songrui) reports the complete Non-harness + RL pipeline. Meetings coordinate shared interfaces, hardware bookings, safety gates, and evaluation conditions. Each team shall confirm one accountable lead before independent development; individual lead assignments remain pending team confirmation.

Progress Blog: Updated weekly with work summaries, code commits, experiment configurations, and logs. Team A records API proposals and automatic decisions; Team B records LLM dialogues and human-approved reward edits. Both record resource usage and deviations from the frozen benchmark for traceability.

Summary Budget:

### Proposed Project Budget #### Itemized Budget Breakdown No.; Budget Item and Included Components; Qty; Procurement Source; Budget (SGD). 1; Yahboom STM32 Self-Balancing Robot & Expansion Packages; 1 set; Robot package / Expansion-package listing; $220. 2; 12V 2200mAh Lithium Battery Pack & 2A Charger; 1 set; Battery and charger listing; $30. 3; Programming and Communication Accessories; 1 lot; Yahboom Official Tmall Store; $40. 4; Safety and Controlled-Test Materials; 1 lot; Yahboom Official Tmall Store; $50. 5; Replacement and Maintenance Components; 1 lot; Yahboom Official Tmall Store; $60. 6; Data-Logging and Measurement Accessories; 1 lot; Yahboom Official Tmall Store; $40. 7; Shipping, Price Variation, and Contingency; 1 allowance; Marketplace checkout; $60. 8; Cloud LLM API Credits and Token Usage; 1 allowance; Direct API provider / Approved institutional billing; $500. Total; Total Planned Budget; —; —; $1,000. #### Budget Category Summary Budget Category; Allocation (SGD); Percentage (%); Purpose & Scope. Robot Platform & Expansion Packages; $220; 22%; Main underactuated robot hardware setup. Batteries, Accessories, Spares & Contingency; $280; 28%; Peripherals (Items 3–6), power supply (Item 2), and shipping/contingency (Item 7). Cloud LLM API Usage; $500; 50%; Model inference fees, prompt optimization, and evaluation. Total Project Budget; $1000; 100%.

Initial High-Level Risks:

Risk 1 Pipeline A LLM Latency and Interface Failure

LLM response delays or invalid outputs can interrupt automatic tuning but must not block the 200 Hz STM32 loop (5 ms period). Run API calls asynchronously off-board, validate schemas and parameter bounds, and retain the current validated controller on failure. Configure and log request timeouts; the existing 5-second safeguard may be used initially. Model choices such as Llama 3.1 8B via Ollama and GPT-4o are experimental configurations and must be recorded. Reused proposals must pass current validation.

Risk 2: Hardware Damage During Testing

Hardware tests in either pipeline can damage components or interrupt the schedule. Validate candidate parameters and PPO policies in simulation and complete transferability checks before supervised deployment. Enforce PWM and angle limits, emergency stop, and baseline fallback. Characterise a safe staged deployment procedure before reducing actuation amplitude; any soft-start setting must preserve the ability to balance. Retain the budgeted maintenance reserve and schedule shared hardware access.

Risk 3 Pipeline A Tuning Non Convergence

Unproductive tuning can consume time and API credits without improving performance. Define the failed-iteration limit N before each run, retain the best validated parameters, and stop or roll back after N unsuccessful iterations. Establish inner balance-loop stability before tuning the outer velocity loop, keep parameter changes bounded, and screen candidates in simulation. Record failures and provide operator override.

Risk 4 Pipeline B Training Failure and Transfer Gap

LLM-suggested rewards may exploit the simulator, destabilise learning, or fail on hardware. Researchers review and version every change; compare reward variants with matched architecture, budget, and seeds. Evaluate physical metrics, use domain randomisation, and validate timing and bounded residual output before deployment. Keep the common PID frozen, record fallback events, and retain all unsuccessful runs. Hardware tests proceed only within characterised recoverable limits.

Risk 5 Shared Platform Changes and Confounded Comparison

Interface drift, competing hardware bookings, or different evaluation conditions can delay one team or invalidate comparisons. Freeze and version the common foundation, agree hardware slots at weekly meetings, and repeat affected tests after approved changes. Report within-pipeline controls separately from the comparison of complete approaches; do not infer a harness-only effect from different control algorithms.

| Summary Milestones | Target Date |
| --- | --- |
| M1 Common PC-robot communication and telemetry schema | Sept. 9, 2026 |
| M2 Common PID, safety, model and platform interface freeze | Sept. 16, 2026 |
| M3 Team A harness and feature-extractor prototype | Sept. 23, 2026 |
| M4 Team B PPO baseline and human-designed reward | Sept. 23, 2026 |
| M5 Team A initial automatic tuning validation in simulation | Oct. 7, 2026 |
| M6 Team B initial LLM-assisted reward training and evaluation | Oct. 7, 2026 |
| M7 Both deployment validations, within-pipeline controls and common comparison | Oct. 23, 2026 |
| M8 Both teams complete common robustness tests | Oct. 23, 2026 |
| M9 Final report delivery | Oct. 30, 2026 |

RACI Chart

| RACI Chart | Person (In alphabetical order) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity | Jiang Li | Jiayi | Songrui | Sridhar | Tze Jun | Yuxin |
| Assemble and verify the balance bot hardware | R | R | R | R | R | R |
| Organize regular meetings and minute the meetings. | I | I | R/A | I | I | I |
| Experimental equipment purchasing and management | I | I | A | I | I | I |
| Team A harness and PID/LQR controller development | C | C | C | R | R | R |
| Team B non-harness reward design and PPO training | R | R | R | C | C | C |
| Within-pipeline results and common approach comparison | R | R | R | A | R | R |
| Final Report writing | R | R | R | R | R | R |
| Common baseline, interfaces and safety validation | R | R | R | R | R | R |
| Team A simulation validation and deployment | C | C | C | R | R | R |
| Team A manual versus LLM tuning and robustness trials | C | C | C | R | R | R |
| Team B policy validation and deployment | R | R | R | C | C | C |
| Team B human versus LLM rewards and robustness trials | R | R | R | C | C | C |

# Revision Map

Revision dated 4 September 2026. Yellow highlighting marks revised or added text; anchored Word comments explain the reasons. Unhighlighted project information and budget values retain their original content. This marked copy contains replacement text, not Word tracked deletions.

## Purpose and Project Description

Assigned Harness + PID/LQR to Team A and Non-harness + RL to Team B. Defined the LLM integration boundary, independent delivery, and limits of cross-pipeline conclusions.

## Requirements and Architecture

Specified the automated tuning loop and researcher-mediated reward workflow. Froze the common PID for RL residual control. Made short-window adaptation and multi-skill control optional.

## Objectives and Evaluation

Added manual-versus-LLM tuning and human-versus-LLM reward controls, resource and effort records, fallback accounting, and matched training conditions. Kept performance improvement figures as research targets.

## Schedule and Responsibilities

Aligned all objectives with M1-M9 and the existing calendar dates. Removed inconsistent academic week labels. Kept existing team membership and expanded RACI tasks to cover validation, deployment, and evaluation.

## Risks and Timing

Unified the control timing at 200 Hz with a 5 ms period. Added RL training and transfer risks, common-interface management, and comparison limitations. Corrected the inner/outer-loop tuning sequence and qualified soft-start settings.

## Items for Team Confirmation

Confirm one accountable lead for Team A and one for Team B before independent development; no new individual appointments have been made. Retain the original comparison lead (Sridhar) and meeting lead (Songrui). Academic week mapping can be added after the teaching calendar is confirmed.

## RACI Legend

R = Responsible for execution; A = Accountable for the outcome; C = Consulted; I = Informed. Existing RACI assignments are retained except for clarified activity names and explicitly added tasks. The original purchasing row has no R assignment; the team should confirm its executor.